## Howto_About
Welcome to the Phased Implementation Gantt Chart Template!
Instructions:
1. Go to the 'Gantt Chart' tab to enter your project tasks.
2. Use dropdowns in the 'Status' column to track progress.
3. Timeline cells will auto-fill based on Start Week and Duration.
4. Refer to the 'Dashboard' tab for project insights.
5. Use the 'Branding' tab to customize with your company logo and contact info.
6. For simplicity, Dependencies are linear, but the field can be modified.
Note: Formula cells are protected to prevent accidental changes.
Name: | SCADA IMPLEMENTATION TEMPLATE
Contact Info: | email: paola@sbsnw.biz
Website: | www.sbsnorthwest.com

## Gantt Chart
Task Name | Phase | Responsible Party | Dependencies | Status | Start Week | Duration | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14
Stakeholder Engagement | Initiate | Project Manager |  | Not Started | 1 | 1 | ■
Project Governance | Initiate | PMO | Stakeholder Engagement | Not Started | 1 | 1 | ■
Scope Definition | Initiate | Business Analyst | Project Governance | Not Started | 2 | 1 |  | ■
Initial Risk Assessment | Initiate | Risk Manager | Scope Definition | Not Started | 2 | 1 |  | ■
Compliance Review | Initiate | Compliance Officer | Initial Risk Assessment | Not Started | 3 | 1 |  |  | ■
Cross-Disciplinary Review | Assess | Department Heads | Compliance Review | Not Started | 4 | 1 |  |  |  | ■
Site Assessment | Assess | Facilities Team | Cross-Disciplinary Review | Not Started | 4 | 1 |  |  |  | ■
System Assessment | Assess | IT Team | Site Assessment | Not Started | 5 | 1 |  |  |  |  | ■
Solution & Deployment | Plan | Technical Lead | System Assessment | Not Started | 6 | 1 | [5 empty] | ■
Resource Planning | Plan | HR & Procurement | Solution & Deployment | Not Started | 6 | 1 | [5 empty] | ■
Logistics & Compliance | Plan | Legal & Logistics | Resource Planning | Not Started | 7 | 1 | [6 empty] | ■
Go-Live Preparation | Execute | Operations | Logistics & Compliance | Not Started | 8 | 1 | [7 empty] | ■
Deployment | Execute | Implementation Team | Go-Live Preparation | Not Started | 9 | 1 | [8 empty] | ■
Handover | Execute | Operations | Deployment | Not Started | 10 | 1 | [9 empty] | ■
Administrative Closure | Close | PMO | Handover | Not Started | 11 | 1 | [10 empty] | ■
Project Review | Close | Project Team | Administrative Closure | Not Started | 12 | 1 | [11 empty] | ■

## Dashboard
Phase | % Complete
Initiate | 0.0%
Assess | 0.0%
Plan | 0.0%
Execute | 0.0%
Close | 0.0%
Number of Tasks Delayed | 8
Upcoming Milestones
Task Name | Phase | Start Week
Solution & Deployment | Plan | 6
Resource Planning | Plan | 6
Logistics & Compliance | Plan | 7
Go-Live Preparation | Execute | 8
Version | 1.0
Last Updated | 2025-08-19